## Liaison Group version
Rangitāiki -Tarawera River Scheme: 2014-2015 Maintenance Works Plan & Estimated Costs
2015-02-24
Reach | Works Description | Work Type- Location | AMP Annual Budget | Map Ref | Status | Costs To Date
Reach 1 Rangitaiki
Mouth to Edgecumbe
| Weed spraying Riverbank | Riverbank Weed spraying | 2587 |  |  | 4152
|  | Fonterra, EastPac ,Paddys lucene |  | R/B 10.6
|  | Various FD sites |  | R/B & L/B
|  | S/Bank. Gorse,B/Berry |  | R/B & L/B | ongoing
|  | Frasers |  | LB 12.9 t0 17.6 | completed
| Layering 1/6 of the reach | Willow /River Bank Maintenance | 7155 |  |  | 9960
|  | Leamings 700mts |  | L/B 6.4 | Completed
|  | Webb 300mts |  | R/B 7.7
River Bank
G Monks - Reids central
|  | Rock Replenishment | 56296 |  |  | 47688
|  | Thornton Rd LB ( V D Topps Lease) |  | 0.8 - 1.9km
|  | Laws Corner |  | 5.8 km
| Fence maintenance. Replace 10% per reach | Fencing | 9502 |  |  | 10008
Campbells ( C Fraser)
| Minor floodgates. Inspect all. | Minor floodgates Inspection/Maint | 780 |  |  | 5413
|  | S/Bank Mowing |  |  | ongoing
|  | Various |  | LB & RB
Seepage Outlets Inspections/Maintenance
|  | Stopbank Maint | 3050 |  |  | 4998
|  | Laws Corner |  | LB 5.8 | Completed
Fertise lease areas
|  | Planting | 4847 |  |  | 3109
|  | Ruiters |  | LB 7.8 | Completed
|  | Monks RB - Manuka Planting |  |  | Completed
Pest Control
|  | Various |  | LB & RB | ongoing
Reach 2 Rangitāiki
Edgecumbe to Te Teko
| Weed spraying Riverbank | Riverbank Weed spraying | 2911 |  |  | 5661
|  | Various F/D sites - gorse,B/berry |  | LB & RB
Stopbank spraying Gorse,B/Berry
|  | Campbell/Fraser |  |  | completed
| Layering 1/6 of the reach | Willow /River Bank Maintenance | 9766 |  |  | 30022
|  | Putuwaki Trust Remove Blue gum |  | LB 16.3 | Completed
|  | Ngatiawa Farms 300m |  | RB 18.0 | Completed
|  | Ngatiawa Farm,Martins 900m |  | RB 19.8 | Completed
|  | Ngatiawa Farms Remove Blue Gums |  | RB 18.7 | Completed
S/Bank Mowing
|  | Edge TeTko Rd |  | Various | completed
|  | Planting | 5615 |  |  | 19594
|  | Ngatiawa,Martans 900m Pole planting. |  | RB 19.8 | completed
|  | WanikauTrust -Manuka Trial |  | RB 18.9 | completed
| Fence maintenance. Replace 10% per reach | Fencing | 8848 |  |  | 5449
|  | Warbricks 1700m |  | RB 16.0
|  | Campbell/Fraser |  |  | completed
|  | Rock | 59984
| Minor floodgates. Inspect all. | Minor floodgates Inspection/Maintenance | 780
|  | Seepage outlets |  | Lb & RB
|  | Stop Bank Maintenance | 3050 |  |  | 3170
|  | Lawrence |  | RB 13.6
|  | Ngatiawa Farms Mulch S/Bank |  | RB 18.6 | Completed
Pest Control
|  | Various S/Bank control |  | L&RB | ongoing
Reach 3 Rangitāiki
Te Teko to Matahina
| Weed spraying Riverbank | Riverbank Weed spraying | 2911 |  |  | 5755
|  | Various F/Damage Repairs,[Willow,Goarse,B/Berry] |  | LB&RB
| Tree clearing 1/15 of the reach | Willow /River Bank Maintenance | 13195 |  |  | 132
Burning
|  | Neweys |  | LB 24.3
|  | Planting | 8939 |  |  | 1600
|  | TeTeko Rugby club |  | LB24.0 | Completed
|  | Poanagas |  | RB25.8 | Completed
|  | Rock | 33423
| Fence maintenance. Replace 10% per reach | Fencing | 1777
Stop Bank Maintenance
F/Gate, Culvert Main
Reach 4 Rangitāiki
Waiohau Valley
| Weed spraying Riverbank | Riverbank Weed spraying | 1201 |  |  | 651
Waikokopu Stream Regen
|  | Wilsons Rock works |  | Various | Completed
| Layering 1/6 of the reach | Willow Maintenance | 13009
Waikokopu Stream Mulching
|  | Carters Lease, 200m |  | RB 52.5
|  | Wilsons 100m Top,Layer,Pole Plant,Fence |  | RB46.1
|  | Wilsons 100m Top/Layer |  | RB 47.6
|  | Planting | 8812 |  |  | 672
Waikokopu Stream Riparian Plan
|  | Rock | 22282
|  | Fence Maintenance |  |  |  | 789
Reach 5 Rangitāiki
Aniwhenua to Murupara
| Weed spraying Riverbank | Riverbank Weed spraying | 3072 |  |  | 450
| Layering 1/6 of the reach | Willow/River Bank Maintenance - Clearing/Layering/planting | 22394 |  |  | 37839
|  | Ngatimanawa 800m Mulching Fence line |  | RB 91.0 | completed
|  | Nivans Willow Topping 500m |  | RB 81.1
|  | Healys TW 40m |  | LB 71.3
|  | Chynoweth Top Willows/Layer 200m |  | RB 71.4
|  | Chynoweth Top Willows 200m |  | RB71.9
|  | Bridgemans Top Willows 400m |  | LB 74.9
|  | Bridgemans Top Willows 300m |  | LB 75.1
|  | Bridgemans Top Willows 200m |  | LB 75.7
|  | Bridgemans TopWillows 200m |  | LB 76.0
|  | Magee Top/Layer Willows 200m |  | RB76.5
|  | Magee Top/Layer Willows 150m |  | RB 77.1
|  | Silcock Top Willows 300m |  | RB 85.7 | Completed
|  | Ngatimanawa Top Willows 900m,TW 20m |  | LB87.5 | Completed
|  | Planting | 15170 |  |  | 1945
|  | Fencing |  |  | completed | 14270
Burning
|  | Healys ,Old Piles |  | LB
|  | Rock Replenishment | 1020
|  | Niven 10m on end of old rock job |  | RB 79.7
Reach 6 Galatea |  | Channel / Beach Alignment
Horomanga, Ohutu, etc
| Layering 1/6 of the reach | Channel/riverbank Weed Spraying | 11000 |  |  | 5987
|  | Horomanga,Ohutu Etc |  | Various | completed
|  | Willow Maintenance | 23300
| Rock maintenance 25% every 15 years | Horomanga Layer Willows
| Rubble maintenance 1/10 of reach | Planting |  |  | completed | 4975
1600
Fence Maintenance
|  | Rock Replenishment | 3450
Reach 7 Whirinaki
|  | Channel/riverbank Weed Spraying | 3611 |  | completed
|  | Willow Maintenance/River Bank Maintenance | 8792 |  |  | 54885
|  | Browns 80m TW |  | RB 2.3
|  | Ngatimanawa 80m |  | LB 0.5 | Completed
|  | Planting | 5965 |  |  | 400
|  | Fence Maintenance |  |  | completed | 1356
Reach 8 Tarawera
Mouth to SH 30
|  | Riverbank Weed spraying | 4227 |  |  | 2886
|  | Various F/Damage Repairs[ Goarse,Willow ,B/Berry |  | L&RB
|  | POA spraying hard corners, Various[Jetboat] |  | L&RB
| Rubble maintenance 1/10 of reach | S/Bank, Gorse,Pampass,B/Berry |  | L&RB
|  | Planting | 742 |  |  | 1200
Pest Control
| Layering 1/6 of the reach | Various |  | L&RB
|  | Willow Maintenance/River Bank | 1096
|  | Burts Wattles |  | LB 2.2
|  | Van Beeks Willows 400m |  | RB 3.5
|  | Verbicas Willows 500m |  | LB 8.7
|  | Helyar Willows1000m |  | RB16.6
| Fence maintenance. Replace 10% per reach | Wilsons 300m |  | LB 16.9
|  | Rock Replenishment | 21756
|  | Fencing | 808
|  | Minor floodgates Inspection/ Maint | 780
|  | Various F/Damage Repairs[ Goarse,Willow ,B/Berry |  | L&RB
Weed spraying Riverbank
| Layering 1/6 of the reach | Stop Bank Maintenance | 2250
Fertilise Lease Areas.
Reach 9 Tarawera
| Rock maintenance 25% every 15 years | Riverbank Weed spraying | 2495
Upstream SH 30
|  | Willow Maintenance | 13094
SH 30 Bridge - Mulching
|  | Planting | 8872
|  | Rock | 11579
|  | Fencing | 304
Reach 10
Old Rangitaiki Channel
| Normal inspection | ORC
|  | Pump Inspection/Maintenance | 8642 |  | ongoing | 4136
|  | Floodgates | 3764 |  | ongoing | 1602
|  | Electricity | 1402
Awaiti Floodgates | Normal inspection | Desilting/Maintenance | 5828 |  |  | 1407
Stopbanks | Minor floodgates. Inspect all.
|  | Riverbank Weed spraying | 1733 |  |  | 48
Rock/Rubble
|  | Stop Bank Misc Maintenance | 3255
Section 109 Access
|  | Minor floodgates Inspection/Maint | 1512 |  | ongoing | 2822
|  | Total Estimated costs | 472633
|  | Works Costs to Date |  |  |  | 296631
|  | Annual Flood Repair Allowance | 180000
Flood Damage
|  | G Monks Reids Central |  | LB 0.1
|  | Chase 80m |  | LB 21.4
|  | Above Rail Bridge 80m |  | LB 6.1
|  | Van Den Topp Lease |  | LB 1.5 to 2.0
|  | Niven 2004 F/Damage Repairs |  | RB 81.4
|  | Tarawera SH 30 - 20 m |  | LB 6.1
|  | Ngatimanwa 80m TW |  | LB 88.6 | completed | 28858
Total Estimated costs including Routine Maintenance and Flood Damage. |  |  | 652633 |  |  | 325489
Note on D116: Andrew Pawson: