## June 2009- old
Rangitaiki River Geotechnical Works as at May 2009
Site No. (file #) | Geotechnical Report  (Received) | Section/Description | Location | Status | Remedial Measures
1 |  | D/s Reids Confluence | RB 800 - 890 | Works Complete
2a |  | Van den Top-Phillips | LB 1700 - 2150 | Works Complete | Filled drain at stopbank toe
2b | July 2007 Report | Moore road seepage | LB 1620-1900 | Investigation complete | Salt water intrusion to low basin. Also concern that there could be further areas downstream and opp. Side of river Report completed.
3 |  | Thornton School | RB 2300 - 2650 | Under investigation | Possible seepage along water main under river.
4 |  | Thornton Floodwall | RB 2900 | Works Complete | Possible seepage - Site ok | <= Is this the same job? Or is there still seepage investigation required over a longer length?
5 | Section 11 | East Bank Road Floodwall | RB 2900 - 3200 | Works Complete | Stability and seepage. Wall joints, foundations and old pipe fixed.
6 |  |  | LB 3480 - 3560 | Works Complete | Possible slump (Rivers & Drainage)
7 |  |  | LB 3720 - 3790 | Works Complete | Rock protection
8 |  | Greig Road Floodwall | LB 3800 | Works Complete | Replace joints and grout foundations
9 |  |  | LB 3960 - 4150 | Works Complete | Rock protection
10 |  | Reynolds Bend | RB 4200 - 4600 | Under Investigation | Possible seepage area Reynolds Bend (Ice Construction)
11 | Section 4 | Langdons | RB 4899 - 6300 | Investigation Complete | Report Complete - Relief Wells and Overlay
11a | Part section 4 above | Langdons berm | RB 5650 - 5870 | Under investigation | Beach removal
12 |  | Langdons edge erosion | RB 5250 - 5350 | Works Complete | Slumping - Erosion repair
13 |  | Laws Bend | LB 5340 - 5800 | Works Complete | Rock protection and stopbank raising
15 |  | U/s of Langdons | RB 6400 - 7350 | To be investigated | Possible seepage area
16 |  | Schlepers | LB 7320 - 7550 | Works Complete | Rock protection | <= stopbank topped up???
17 |  | Downstream Go cart Track | LB 8100 - 8200 | Works Complete | Rock protection
18 |  | Downstream Go cart Track | LB 8200 - 8240 | Works Complete | Rock protection | <= rubish dump backfilling??
19 |  |  | RB 8380 - 8450 | Works Complete | Rock protection
20 |  |  | RB 8530 - 8610 | Works Complete | Rock protection
21 |  |  | RB 8660 - 8730 | Works Complete | Rock protection
22 | Section 12 | Opp. Soldiers Road | RB 8950 - 9100 | To be investigated | Seepage analysis still to be done
23 | Section 2  | Upstream Edgecumbe Domain | LB 9100 - 9300 | Works Complete | Pressure relief trench
24 |  | Opp. Tanekaha St | RB 9280 - 9370 | Under investigation | Slumping & erosion. Marianne unconcerned. Tony to inspect
25 | Section 15  | Hendl's to Tanekaha St | LB 9300 - 10150 | Works Complete | Tree clearing, berm reinstatement and rockworks
25a | Section 15 continued  | Concrete floodwall | LB9360-9720 | Works Complete | Floodwall seepage cutoff wall completed
26 |  |  | RB 9310 - 9440 | Works Complete | Old effluent pond filled in
27 |  |  | LB 9420 - 9510 | Works Complete | Rock protection
28 | 63A College Road  | 63A College Road (Hendl's) | LB 9820 - 9970 | Works Complete | Overlay on town side of stopbank
29 | Section 14  | 35 College Rd to Hendl's | LB 10150 - 10300 | Works Complete | Pressure relief trench and tree clearing completed
30 | Section 1 | 35 College Road | LB 10300 - 10400 | Works Complete | Sheet piling
30a |  | 35 College Road berm works | LB 10350 -10600 | Works Complete | Rock berm
31a |  | 43 College Rd - Hole investigation | LB 10350 -10450 | Works Complete | Depression/hole investigated. Stormwater pipe fault found. Repair completed.
32 |  | College Road | LB 10450 - 10600 | Works Complete | Rock berm
33 | Section 13  | SH2 to Riverslea Floodwall | LB 10600 - 11200 | Works Complete | Pressure relief trenches, overlays & subsoil drains complete. S/b heights checked & OK. Tennis court retaining wall completed.
33a |  | Upstream of Riverslea Wall | LB 10400 - 10600 | Works Complete | Stripdrain completed
34 |  | Fonterra | RB 10720 - 11190 | Works Complete | Rock protection
36 |  |  | LB 11150 - 11250 | Works Complete | Rock protection
37 | Section 5  | Kowhai Av. to SH2 (part of Ngaio Place works) | LB 11200 - 11500 | Works Complete | Pressure relief trench, overlay & tree stump 1m overlay. S/b height checked and OK.
37a |  | Upstream Rail bridge | LB 11300 - 11450 | Investigation complete | Berm reinstatement & rock works on river bank- 2009 -2010
38 | New section | Miro Place | RB 11200 - 11850 | Works Complete | Coal concern re seepage. Flyash concern re contamination.
38a |  | Miro Place - Berm Works | RB 11200 - 11850 | Works Complete | Debris pile on berm removed. Mound beneath bridges may be used for works later.
38b |  | SH2 & Rail Bridge stopbank | RB11150-11180 | Works Complete | Raise stopbank between bridges. Marianne concern re sand layers
39 | Section 3  | Ngaio Place Section (Fert works to Kowhai Av.) | LB 11500 - 12200 | Works Complete | Pressure relief trench, wells (Ngaio Place) and overlay completed.
40a | Part Section 6  | Hydro Road (Wayne Howe) | RB11870-11920 | Works Complete | Drain trench
41 |  | Downstream of Transpower | RB 11600 - 12260 | Works Complete | Rock protection-bank erosion minimum, size berm
42 | Section 6  | Downstream of Transpower | RB 11850 - 12300 | Investigation complete | New Transpower .33% AEP to be investigated
|  | Downstream of Transpower | RB 11700 - 11900 | Works Complete | Seepage relief wells on Hydro Road complete
43 | Section 10 | Otakiri Road area | LB 12200 - 12700 | To be investigated | Seepage and stability
44 |  | Adjacent Transpower site | RB 12260 - 12460 | Works Complete | Rock protection
45 |  | Transpower | RB 12300 - 12640 | Works Complete | Toe loading
46 |  | Black’s Farm | RB 12640 - 13000 | Works Complete | Toe loading
46a | Email 10-9-07 | Black’s Farm | RB 12850 | No works required | Wet area investigated - no works required (Marianne email of 10-9-07)
47 |  |  | LB 12890 - 13010 | Works Complete | Rock protection
48 |  | Sullivan’s Breach | RB 13000 - 13330 | Works Complete | Toe loading
49 | Section 8 | Black's Farm Area | LB 13000 - 13500 | To be investigated | Seepage
49a |  | Campbell's Corner | LB 14100 - 14350 | Under investigation | Seepage - Berm construction/rock lining S/B stability 2009-2010
50 | Section 9 | U/s of Sullivan's | RB 13600 - 13800 | To be investigated | Seepage (old meander course?)
51 |  |  | RB 14570 - 14860 | Works Complete | Rock protection
52 |  |  | RB 15090 - 15410 | Works Complete | Rock protection
53 |  | Kokohinau Bend | LB 15230 - 15870 | Works Complete | Rock protection
53a |  | Kokohinau Bend (rock repair) | LB 15870 - 16000 | Under investigation | Seepage concern at original repair site
54 |  | Kokohinau Bend | LB 16000 - 16230 | Works Complete | Rock protection
55 |  |  | RB 16870 - 17020 | Works Complete | Rock protection
56 |  |  | LB 17590 - 17740 | Works Complete | Rock protection
57 |  |  | LB 17850 - 17900 | Works Complete | Rock protection
58 | Section 7 | Pryor | LB 17600 - 18000 | Under investigation | Seepage and stability (PLB tomo hole etc)
59 |  |  | RB 18790 - 19120 | Works Complete | Rock protection
60 |  | Collier's | LB 20210 - 20370 | Works Complete | Rock protection
61 |  | Omataroa Orchard | RB 20450 - 20670 | Works Complete | Rock protection
62 |  | Walkers | RB 20670 - 21030 | Works Complete | Rock protection
63 |  | Maniapoto | LB 21110 - 21210 | Works Complete | Rock protection
64 |  | Chase | LB 21270 - 21440 | Works Complete | Rock protection
65 |  | M Ramanui | LB 21620 - 21800 | Works Complete | Rock protection
66 |  | In No.65 above | LB 21820 - 22010 | Works Complete | Rock protection
67 |  |  | RB 22510 - 22630 | Works Complete | Rock protection
68 |  | Te Teko Marae | RB 22740 - 22990 | Works Complete | Rock protection
69 |  | Downstream Te Teko | LB 23390 - 23740 | Works Complete | Rock protection
70 |  | Cableway | LB 24170 - 24400 | Works Complete | Rock protection
71 |  | Eastern Drain stopbanks |  | Works Complete | Stopbank strengthening and seeage control works
72 |  | Te Rahu Canal (Barrs) |  | Investigation complete | Works to be included in TYP 2009
73 |  | Omeheu Canal (Richardson's) | RB 3600-3700 | Works Complete | Toe loading of seepage area
74 |  | Reids Central Canal | LB 2320-2740 | To be investigated | Seepage concern
75 |  | Reids Central Canal Rbank | RB 1500- 1700 | Investigation complete | Seepage concern - Cut off drain & overlay
76 |  | Rangitaiki R Thornton Rd | R Bank | To be investigated | Seepage concern
Overall Progress Stats at 31 January 2008:
79 Rangitaiki sites listed (Excluding "Other sites")
32 sites (approx) that were "2004 Flood recovery works"
Therefore 47 geotechnical remedial jobs overall
15 still to be investigated/under investigation
5 Investigation complete
1 in progress
Therefore 26 geotech jobs have been completed

## August 2009
Rangitaiki River Geotechnical Works Schedule as at August 2009
Note: 2004 flood repair works sites removed from schedule
Site No. (file #) | Geotechnical Report  (Received) | Section/Description | Location | Job Code | Status | Remedial Measures
76 |  | Rangitaiki R Thornton Hall Rd | RB 800-1000 |  | To be investigated | Seepage concern
77 |  | Rangitaiki R Thornton Hall Rd | RB1500-1900 |  | To be investigated | Seepage concern
2a |  | Van den Top-Phillips | LB 1700 - 2150 | PHILLIPV | Works Complete | Filled drain at stopbank toe
2b | July 2007 Report | Moore Road seepage | LB 1620-1900 |  | Investigation complete | Salt water intrusion to low basin. Also concern that there could be further areas downstream and opp. Side of river . Report completed.
3 |  | Thornton School | RB 2300 - 2650 |  | Under investigation | Possible seepage along water main under river.
5 | Section 11 | East Bank Road Floodwall | RB 2900 - 3200 | RT1WALLS | Works Complete | Stability and seepage. Wall joints, and foundations grouted to reduce seepage
8 |  | Greig Road Floodwall | LB 3800 | RT1WALLS | Works Complete | Stability and seepage. Wall joints, and foundations grouted to reduce seepage
10 |  | Reynolds Bend | RB 4200 - 4600 |  | Under Investigation | Possible seepage area Reynolds Bend
11 | Section 4 | Langdons | RB 4899 - 6300 |  | Investigation Complete | Report Complete - seepage relief wells and overlay
11a | Part section 4 above | Langdons berm | RB 5650 - 5870 |  | Under investigation | Beach removal
15 |  | U/s of Langdons | RB 6400 - 7350 |  | To be investigated | Possible seepage area
22 | Section 12 | Opp. Soldiers Road | RB 8950 - 9100 |  | To be investigated | Seepage analysis still to be done
23 | Section 2  | Upstream Edgecumbe Domain | LB 9100 - 9300 |  | Works Complete | Pressure relief trench
24 |  | Opp. Tanekaha St | RB 9280 - 9370 |  | Under investigation | Slumping & erosion. Marianne unconcerned. Tony to inspect
25 | Section 15  | Hendl's to Tanekaha St | LB 9300 - 10150 | COLTANE | Works Complete | Tree clearing, berm seepage cut-off and rockworks
25a | Section 15 continued  | Concrete floodwall | LB9360-9720 | COLTANE | Works Complete | Floodwall seepage cutoff nib-wall completed
28 | 63A College Road  | 63A College Road (Hendl's Subdivision) | LB 9820 - 9970 |  | Works Complete | Overlay on town side of stopbank
29 | Section 14  | 35 College Rd to Hendl's | LB 10150 - 10300 | COLHENDL | Works Complete | Pressure relief trench and tree clearing completed
30 | Section 1 | 35 College Road | LB 10300 - 10400 | MILNEHRW | Works Complete | Sheet piling for seepage cutoff
30a |  | 35 College Road berm works | LB 10350 -10600 | COLLEGER | Works Complete | Rock protection/berm seepage cut-off
32 |  | College Road | LB 10450 - 10600 | COLLEGER | Works Complete | Rock protection/berm seepage cut-off
33 | Section 13  | SH2 to Riverslea Floodwall | LB 10600 - 11200 | COSSIECL & EDGETCRT | Works Complete | Pressure relief trenches, overlays & subsoil drains complete. Tennis court retaining wall completed.
33a |  | Upstream of Riverslea Wall | LB 10400 - 10600 | COLLWALL | Works Complete | Seepage stripdrain completed
37 | Section 5  | Kowhai Av. to SH2 (part of Ngaio Place works) | LB 11200 - 11500 | NGAIOPLG | Works Complete | Pressure relief trench and 1m overlay.
37a |  | Upstream Rail bridge | LB 11300 - 11450 |  | Investigation complete | Berm reinstatement & rock works on river bank- 2009 -2010
38 | New section | Miro Place | RB 11200 - 11850 | MIROPLOL | Works Complete | Coal concern re seepage. Toe loading
38a |  | Miro Place - Berm Works | RB 11200 - 11550 | MIROBERM | Works Complete | Debris pile on berm removed. Mound beneath bridges removed
38b |  | SH2 & Rail Bridge stopbank | RB11150-11180 | MIROBERM | Works Complete | Raise stopbank between bridges. Marianne concern re sand layers
38c |  | Hydro Road seepage wells | RB11700-11900 | HYDROWEL | Works Complete | Seepage relief wells on Hydro Road complete
39 | Section 3  | Ngaio Place Section (Fert works to Kowhai Av.) | LB 11500 - 12200 | NGAIOPLG | Works Complete | Pressure relief trench, wells (Ngaio Place) and overlay completed.
40a | Part Section 6  | Hydro Road (Wayne Howe) | RB11870-11920 |  | Works Complete | Seepage relief trench
41 | Section 6  | Downstream of Transpower | RB 11600 - 11950 | TRANSRBR | Works Complete | Rock protection/berm seepage cut-off
41a |  | Downstream of Transpower | RB 11600 - 12260 | TRANSPOL | In progress | Toe-loading overlay works - multple sites. Drainage and topsoiling to complete.
41b |  | Transpower to Miro Pl. | RB 11600 - 11950 | MIROTRAS | Works Complete | Stopbank seepage control works
42 | Section 6  | Downstream of Transpower | RB 11850 - 12300 |  | Investigation complete | New Transpower .33% AEP to be investigated
43 | Section 10 | Otakiri Road area | LB 12200 - 12700 |  | To be investigated | Seepage and stability
46a | Email 10-9-07 | Black’s Farm | RB 12850 |  | No works required | Wet area investigated - no works required (Marianne email of 10-9-07)
49 | Section 8 | Black's Farm Area | LB 13000 - 13500 |  | To be investigated | Stopbank seepage control works
49a |  | Campbell's Corner | LB 14100 - 14350 |  | Under investigation | Stopbank seepage control works
50 | Section 9 | U/s of Sullivan's | RB 13600 - 13800 |  | To be investigated | Seepage concern (old meander course?)
53a |  | Kokohinau Bend (rock repair) | LB 15870 - 16000 |  | Under investigation | Seepage concern at original repair site
58 | Section 7 | Pryor | LB 17600 - 18000 |  | Under investigation | Seepage and stability (tomo hole etc)
73 |  | Omeheu Canal (Richardson's) | RB 3600-3700 | JROMEHUS | Works Complete | Toe loading of seepage area completed - not on map
74 |  | Reids Central Canal | LB 2320-2740 |  | To be investigated | Seepage concern
75 |  | Reids Central Canal Rbank | RB 1500- 1700 |  | Investigation complete | Seepage concern - Cut off drain & overlay
Note on E16: GNOR
Note on E20: GNOR
Note on E34: GNOR

## May 2014
Rangitaiki River Geotechnical Works Schedule as at 31 May 2014
Note: 2004 flood repair works sites excluded from schedule
Site No. (file #) | Geotechnical Report | Section/Description | Location | Job Code | Status | Remedial Measures
2a |  | Van den Top-Phillips filled drain | LB 1700 - 2150 | PHILLIPV | Works Complete | Filled drain at stopbank toe
2b | July 2007 Report | Perry - seepage - overlay | LB 1620-1900 |  | Works Complete | Salt water intrusion to low basin. Overlay completed 2013
3a |  | Thornton School - Seepage at Braemar water line | RB 2500-2600 |  | Works Complete | Possible seepage along water main under bank. Filter system installed around pipe
3b |  | Thornton School - Berm & rock works | RB 2300 - 2950 |  | Works Complete | complete
3c |  | Shaws/Topps lowland area | RB 2100 - 3100 |  | Under Investigation | Consultation with affected landowners underway but huge issues involved. This work also addresses Site 5 seepage concerns. Consider as part of floodway works
5 | Section 11 | East Bank Road Floodwall | RB 2900 - 3200 | RT1WALLS | Works Complete | Stability and seepage. Wall joints, and foundations grouted to reduce seepage
8 |  | Greig Road Floodwall | LB 3800 | RT1WALLS | Works Complete | Stability and seepage. Wall joints, and foundations grouted to reduce seepage
10 |  | Reynolds Bend: Berm seepage/rockworks | RB 4200 - 4600 |  | Works Complete | Possible seepage area Reynolds Bend.
11 | Section 4 | Langdons: Pressure relief wells | RB 4899 - 6300 |  | Works Complete | Seepage relief wells complete
11a | Part section 4 above | Langdons and Martins (3x overlay) | RB 5650 - 5870 |  | Works Complete | Berm material to be used for overlay work (3 sites, Langdons trees, Langdons access and Martins)
15 |  | U/s of Langdons - overlay | RB 6400 - 7350 |  | Works Complete | seepage concerns - Overlay works
23 | Section 2 | Upstream Edgecumbe Domain - pressure relief trench | LB 9100 - 9300 |  | Works Complete | Pressure relief trench
24 |  | Opp. Tanekaha St | RB 9280 - 9370 |  | No works required | No geotech works required. Required rockworks will be completed as maintenance works.
25 | Section 15 | Hendl's to Tanekaha St | LB 9300 - 10150 | COLTANE | Works Complete | Tree clearing, berm seepage cut-off and rockworks
25a | Section 15 continued | Concrete floodwall | LB9360-9720 | COLTANE | Works Complete | Floodwall seepage cutoff nib-wall completed
28 | 63A College Road | Hendl's Subdivision - overlay | LB 9820 - 9970 |  | Works Complete | Overlay on town side of stopbank
29 | Section 14 | 35 College Rd to Hendl's - pressure relief | LB 10150 - 10300 | COLHENDL | Works Complete | Pressure relief trench and tree clearing completed
30 | Section 1 | 35 College Road - sheet piling | LB 10300 - 10400 | MILNEHRW | Works Complete | Sheet piling for seepage cutoff
30a |  | 35 College Road berm works | LB 10350 -10600 | COLLEGER | Works Complete | Rock protection/berm seepage cut-off
32 |  | College Road | LB 10450 - 10600 | COLLEGER | Works Complete | Rock protection/berm seepage cut-off
33 | Section 13 | SH2 to Riverslea Floodwall - pressure relief | LB 10600 - 11200 | COSSIECL EDGETCRT | Works Complete | Pressure relief trenches, overlays & subsoil drains complete. Tennis court retaining wall completed.
33a |  | Upstream of Riverslea Wall - stripdrain | LB 10400 - 10600 | COLLWALL | Works Complete | Seepage stripdrain completed
37 | Section 5 | Kowhai Av. to SH2 (part of Ngaio Place works) - pressure relief | LB 11200 - 11500 | NGAIOPLG | Works Complete | Pressure relief trench and 1m overlay.
37a |  | Upstream Rail bridge - Main Street | LB 11300 - 11450 |  | Works Complete | Berm reinstatement & rock works completed
38 | New section | Miro Place | RB 11200 - 11850 | MIROPLOL | Works Complete | concern re seepage. Toe loading
38a |  | Miro Place - Berm Works | RB 11200 - 11550 | MIROBERM | Works Complete | Debris pile on berm removed. Mound beneath bridges removed
38b |  | SH2 & Rail Bridge stopbank | RB11150-11180 | MIROBERM | Works Complete | Raise stopbank between bridges. Geotech concern re sand layers
38c |  | Hydro Road seepage wells | RB11700-11900 | HYDROWEL | Works Complete | Seepage relief wells on Hydro Road complete
39 | Section 3 | Ngaio Place Section (Fert works to Kowhai Av.) | LB 11500 - 12200 | NGAIOPLG | Works Complete | Pressure relief trench, wells (Ngaio Place) and overlay completed.
40a | Part Section 6 | Hydro Road (Wayne Howe) | RB11870-11920 |  | Works Complete | Seepage relief trench
41 | Section 6 | Downstream of Transpower | RB 11600 - 11950 | TRANSRBR | Works Complete | Rock protection/berm seepage cut-off
41a |  | Downstream of Transpower (Savage) | RB 11600 - 12260 | TRANSPOL | Works Complete | Toe-loading overlay works - multiple sites. Drainage and topsoiling
41b |  | Transpower to Miro Pl. | RB 11600 - 11950 | MIROTRAS | Works Complete | Stopbank seepage control works
41c |  | Downstream of Transpower | RB 11950 - 12200 |  | No works required | No geotech works required. Required rockworks will be completed as maintenance works.
43 | Section 10 | Otakiri Road area - Vibickas section | LB 12200 - 12700 |  | Works Complete | Berm seepage, rockworks and stopbank seepage cutoff completed
43a |  | Virbickas to Campbells - stopbank seepage | LB 12400 - 14400 |  | Works Complete | Seepage cutoff layer along stopbank completed
46a |  | Black’s Farm | RB 12850 |  | No works required | Wet area investigated - no works required (Marianne email of 10-9-07)
78 | Additional works | Sullivans Bend: seepage relief wells | RB 12900 - 13100 |  | Works Complete | Seepage relief wells and ground water monitoring piezometers
49 | Section 8 | Black's Farm Area | LB 13000 - 13500 |  | Works Complete | Berm seepage, rockworks and stopbank seepage cutoff completed
49a |  | Campbell's Corner | LB 14100 - 14350 |  | Works Complete | Stopbank seepage control works completed | Appendix 3
50 | Section 9 | U/s of Sullivan's | RB 13600 - 13800 |  | Under Investigation | Seepage concern (old meander course?)
53a |  | Kokohinau Bend (seepage trench/overlay) | LB 15870 - 16000 |  | Under Investigation | Seepage concern at original repair site
58 | Section 7 | Pryor | LB 17600 - 18000 |  | Under Investigation | Seepage and stability (tomo hole etc)
73 |  | Omeheu Canal (Richardson's) | RB 3600-3700 | JROMEHUS | Works Complete | Toe loading of seepage area completed - Omeheu Canal not on map
74 |  | Reids Central Canal (Vierbooms) | RB 1500- 1700 |  | Works Complete | Seepage concern - Cut off drain & overlay
75 |  | Reids Central Canal (Shaws) | LB 2320-2740 |  | Works Complete | Seepage concern
76 |  | Rangitaiki R Thornton Hall Rd | RB 800-1000 |  | Under Investigation | Seepage concern.
77 |  | Rangitaiki R Thornton Hall Rd | RB1500-1900 |  | Under Investigation | Seepage concern.
78 |  | Sullivans Bend:seepage relief wells | RB 12900 - 13100 |  | Works Complete | Seepage relief wells and ground water monitoring piezometers
79 |  | Reids Canal Floodway upgrading stage 3 | RCC 0-970m |  | Under Investigation | Drainage wicks and overlays required on both sides of the canal. Alternative is to bund houses and along highway.
80 |  | Reids Canal Floodway stage 2a | RCC 1050-2900LB, |  | Works Complete | Rebuild stopbanks, use overlays and drainage wicks on much of both stopbanks to reduce risk of piping and heave
81 |  | Reids Canal Floodway stage 1 | RCC LB 2950-3650m, RB 2550-3390m |  | Works Complete | Rebuild right stopbank, pressure relief trenches on most of left and right stopbanks at toe. Pressure relief wells at some points
82 |  | Reids Canal Floodway stage 2b | RCC 1050-2550RB |  | Works in Progress | Rebuild stopbanks, use overlays and drainage wicks on much of both stopbanks to reduce risk of piping and heave
Note: Refer to the aerial photo-plan maps attached for locations of works.
Note on E15: GNOR
Note on E19: GNOR
Note on E33: GNOR